## Project tracker
Project tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Project | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Task 1 | Document Assebly | Davis | 2025-02-01 | 2025-04-17 | 126 | 76 | 2024-11-23 | 2025-01-27 | 300 | 64
Task 2 | Data Collection | Davis | 2025-02-10 | 2025-03-08 | 28 | 28 | 2024-12-17 | 2025-01-20 | 390 | 33
Task 3 | Data Integration | Davis | 2025-03-08 | 2025-04-17 | 35 | 39 | 2024-10-19 | 2024-12-31 | 500 | 72
Task 4 | Thesis Defense | Davis | 2024-10-29 | 2024-11-08 | 250 | 9 | 2024-10-29 | 2024-11-17 | 276 | 18
Task 5 | Empty | Empty | 2024-10-29 | 2024-12-08 | 300 | 39 | 2024-10-29 | 2024-12-14 | 310 | 45
Task 6 | Empty | Empty | 2024-11-28 | 2024-12-08 | 500 | 10 | 2024-11-28 | 2024-12-13 | 510 | 15
Task 7 | Empty | Empty | 2024-12-14 | 2025-01-07 | 750 | 23 | 2024-12-14 | 2025-01-12 | 790 | 28
Task 8 | Empty | Empty | 2024-12-19 | 2025-01-27 | 450 | 38 | 2024-12-13 | 2025-01-22 | 430 | 39
Task 9 | Empty | Empty | 2024-10-24 | 2024-11-13 | 250 | 19 | 2024-10-29 | 2024-11-08 | 200 | 9
SETUP

## Setup
Setup
Category Name | Employee Name
Document Assebly | Davis
Data Collection | Empty
Data Integration | Employee 3
Thesis Defense | Employee 4
Empty | Employee 5
Category 6 | Employee 6
PROJECTS